## Sheet1
Product Backlog sample for Social media application
ID | Title | Epic | User Story | Priority (MoSCoW) | Status | Acceptance Criteria | Functional Requirements | Non-Functional Requirements | Original Estimate | Actual Effort (In days)
1 | Prompt Submission Interface | Epic 1: Secure Prompt Handling | As a user, I want to submit prompts through a secure interface so that my requests are processed safely. | Must Have | Completed | Given a user submits a prompt, when the request is received, then the system shall securely transmit it to the processing pipeline. | Secure UI/API interface; session handling; input validation. | Usability, accessibility, secure communication | 3 days | 4 days
2 | Input Preprocessing Module | Epic 1: Secure Prompt Handling | As a system, I want to normalize and tokenize input prompts to prepare them for analysis. | Must Have | Completed | Given a prompt is received, when preprocessing occurs, then the system shall normalize text and remove noise. | Text normalization; tokenization; language detection. | Low latency, accuracy, reliability | 3 days | 3 days
3 | Semantic Analysis Engine | Epic 2: Intent Analysis | As a system, I want to analyze the semantic meaning of prompts to detect malicious intent. | Must Have | Completed | Given a processed prompt, when semantic analysis is executed, then the system shall detect intent and potential policy violations. | NLP models; intent classification; rule‑based checks. | Detection accuracy, performance efficiency | 4 days | 5 days
4 | Behavioral Analysis Module | Epic 2: Intent Analysis | As a system, I want to evaluate interaction patterns to identify suspicious behavior. | Must Have | Completed | Given a sequence of prompts, when behavioral analysis occurs, then unusual interaction patterns shall be identified. | Pattern tracking; anomaly detection algorithms. | Real‑time monitoring, scalability | 4 days | 4 days
5 | Intent Drift Detection Engine | Epic 3: Advanced Attack Detection | As a system, I want to detect changes in user intent across conversation turns to identify multi‑step attacks. | Should Have | In Progress | Given multi‑turn conversations, when intent changes significantly, then the system shall flag potential manipulation attempts. | Context tracking; conversation modeling. | Multi‑turn consistency, analytical precision | 5 days | 6 days
6 | Context Integrity Monitor | Epic 3: Advanced Attack Detection | As a system, I want to verify that system instructions and context are not manipulated. | Must Have | In Progress | Given system instructions exist, when prompts attempt modification, then the system shall detect tampering. | Prompt comparison; instruction protection logic. | Robustness, protection against manipulation | 4 days | 5 days
7 | Risk Scoring Engine | Epic 4: Threat Evaluation | As a system, I want to compute a risk score based on analysis results to classify prompt safety. | Must Have | In Progress | Given outputs from analysis modules, when scoring occurs, then the system shall assign a numerical threat score. | Weighted scoring model; threshold configuration. | Reliability, consistent threat evaluation | 3 days | 4 days
8 | Decision Engine | Epic 4: Threat Evaluation | As a system, I want to decide whether to allow, sanitize, or block prompts. | Must Have | Pending | Given a risk score, when evaluation occurs, then the system shall classify the prompt as safe or malicious. | Decision rules; policy enforcement. | Fast response time, policy enforcement accuracy | 3 days | 3 days
9 | Output Safety Filter | Epic 5: Safe Response Generation | As a system, I want to check generated responses for harmful or sensitive content. | Should Have | Pending | Given generated responses, when validation occurs, then harmful content shall be removed or blocked. | Content filtering; policy compliance checks. | Content safety, compliance, precision | 4 days | 4 days
10 | Logging & Audit Module | Epic 6: Governance & Monitoring | As an administrator, I want all interactions recorded for audit and analysis purposes. | Must Have | Pending | Given system activity occurs, when logging is triggered, then records shall be stored securely for auditing. | Event logging; secure storage; reporting interface. | Data integrity, availability, traceability | 4 days | 3 days