## Sheet1
Sprint Retrospective — PID-Guard (Minor Project)
What went well | What went poorly | What ideas do you have | How should we take action
positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints. | Guidelines | Sprint item 1
The Prompt Input & Preprocessing Module was successfully implemented, including text normalization, tokenization, and encoding handling, ensuring consistent input for downstream processing. | The Behavioral Analysis and Intent Pattern Modules were not fully implemented, limiting detection to single-input analysis rather than session-based behavior. | Extend the detection pipeline into a hybrid architecture combining semantic, behavioral, and statistical features for improved robustness. | In Sprint 2, prioritize completion of Behavioral Analysis, Intent Drift Detection, and Context Integrity Modules to strengthen detection coverage.
The Semantic Analysis Engine was integrated using statistical token probability analysis (GLTR-inspired approach), enabling initial detection of AI-generated patterns. | Detection accuracy of the Semantic Model was low for paraphrased or human-like AI outputs due to lack of dataset diversity and absence of model fine-tuning. | Introduce feature engineering techniques such as perplexity variance, burstiness analysis, and entropy-based scoring to enhance detection accuracy. | Implement a standardized preprocessing pipeline (lowercasing, normalization, UTF-8 encoding, token filtering) to eliminate input inconsistencies.
A functional frontend interface was deployed, allowing end-to-end flow from user input → detection → output visualization. | The Input Preprocessing Module failed in edge cases (long text, special characters), causing inconsistent token distributions and affecting scoring reliability. | Incorporate larger benchmark datasets (e.g., AI-generated corpora, academic datasets) and perform hyperparameter tuning for model optimization. | Allocate dedicated effort for model training, evaluation, and validation, using metrics such as precision, recall, F1-score, and ROC-AUC.